## Deployment Checklist
ID | Area | Task | Required evidence | Owner | Status | Evidence link | Notes
ENV-001 | Environment | Create staging/production .env from templates | Redacted checklist confirmation |  | Not Started
ENV-002 | Environment | Set APP_ENV=production | Screenshot/redacted config note |  | Not Started
ENV-003 | Environment | Set APP_DEBUG=false | Error page check with no stack trace |  | Not Started
SEC-001 | Secrets | Generate real APP_SECRET/session/CSRF secrets | Owner confirmation, no values in docs |  | Not Started
DB-001 | Database | Run migrations/install on staging | Migration log |  | Not Started
DB-002 | Database | Confirm backups | Backup restore test note |  | Not Started
PAY-001 | Stripe | Configure test publishable/secret keys | Readiness screen redacted |  | Not Started
PAY-002 | Stripe | Configure webhook signing secret | Signed webhook event ID |  | Not Started
PAY-003 | Stripe | Configure connected organiser account | Connected account ID redacted/last 4 |  | Not Started
PAY-004 | Stripe | Run signed webhook checkout | Order ID, ticket ID, QR count, ledger evidence |  | Not Started
MEDIA-001 | Media | Enable PHP GD in web runtime | phpinfo or app health evidence |  | Not Started
MEDIA-002 | Media | Configure ClamAV/equivalent scanning | Scan pass/fail evidence |  | Not Started
WEB-001 | Web | Configure HTTPS/SSL | Browser lock and SSL check |  | Not Started
WEB-002 | Web | Protect/remove local showcase/review routes | Route list/security decision |  | Not Started
QA-001 | Human testing | Run P0 human test matrix | Completed workbook |  | Not Started
QA-002 | Human testing | Run mobile/tablet real device tests | Screenshots/videos |  | Not Started
QA-003 | Human testing | Run security negative tests | Issue log and retest evidence |  | Not Started
OPS-001 | Operations | Set logging/monitoring | Alert/log screenshot |  | Not Started
OPS-002 | Operations | Document rollback plan | Rollback checklist |  | Not Started
OPS-003 | Operations | Define event-day support contacts | Support rota |  | Not Started